## Polished_Defect_Log
DEF ID | Summary | Module | REQ ID | TC ID | Severity | Priority | Environment | Steps to Reproduce | Expected Result | Actual Result | Root Cause | Category | Status
DEF-001 | Duplicate home loan application created after double-clicking Submit | Customer & Loan Application | REQ-007 | TC-007-001 | High | P1 | SIT | Submit application twice rapidly | Only one application is created | Two applications are created | Missing idempotency validation | Workflow | Ready for Retest
DEF-002 | Draft application lost after session timeout | Customer & Loan Application | REQ-002 | TC-002-006 | Medium | P2 | SIT | Leave session idle then save draft | Draft is preserved | Draft data is lost | Session state not persisted | Error Handling | Fixed
DEF-003 | Expired ID card accepted during identity verification | Customer Eligibility & Verification | REQ-009 | TC-009-003 | Critical | P1 | SIT | Upload expired ID | Expired ID rejected | Verification succeeds | Business rule missing | Validation | Assigned
DEF-004 | Applicant aged 17 passes eligibility validation | Customer Eligibility & Verification | REQ-010 | TC-010-004 | High | P1 | SIT | Enter DOB under minimum age | Applicant rejected | Application proceeds | Incorrect age comparison | Business Logic | In Progress
DEF-005 | AML screening ignores exact sanctioned match | Customer Eligibility & Verification | REQ-015 | TC-015-001 | Critical | P1 | UAT | Screen sanctioned customer | Application blocked | Customer cleared | API mapping issue | API Integration | New
DEF-006 | Property valuation accepts negative amount | Property Assessment | REQ-021 | TC-021-003 | High | P1 | SIT | Enter -100 valuation | Validation error | Negative value saved | Missing validation | Validation | Assigned
DEF-007 | LTV calculation rounds 80.01% to 80% | Property Assessment | REQ-022 | TC-022-005 | High | P1 | SIT | Loan exceeds policy by 0.01% | Application rejected | Application approved | Incorrect calculation | Calculation | Ready for Retest
DEF-008 | Agricultural land incorrectly eligible as collateral | Property Assessment | REQ-020 | TC-020-005 | Medium | P2 | UAT | Select agricultural land | Rejected | Accepted | Business rule missing | Business Logic | Fixed
DEF-009 | Credit score 520 incorrectly approved | Credit Assessment & Approval | REQ-025 | TC-025-005 | Critical | P1 | SIT | Assess low credit score | Loan declined | Loan approved | Threshold configuration | Business Logic | Assigned
DEF-010 | DTI 40.35% incorrectly approved | Credit Assessment & Approval | REQ-026 | TC-026-005 | Critical | P1 | SIT | Income 20M debt 8.07M | Application rejected | Application approved | Wrong comparison operator | Calculation | In Progress
DEF-011 | Interest engine ignores promotional rate | Credit Assessment & Approval | REQ-028 | TC-028-005 | High | P2 | UAT | Apply promo customer | Promo rate applied | Standard rate used | Rule priority defect | Calculation | New
DEF-012 | Loan activated before disbursement confirmation | Contract & Disbursement | REQ-040 | TC-040-003 | Critical | P1 | SIT | Activate before funds transfer | Activation blocked | Loan activated | Workflow sequencing | Workflow | Assigned
DEF-013 | Duplicate disbursement after browser refresh | Contract & Disbursement | REQ-038 | TC-038-003 | Critical | P1 | SIT | Refresh after submit | Single payment | Funds transferred twice | Missing duplicate check | Workflow | Fixed
DEF-014 | Expired digital certificate accepted | Contract & Disbursement | REQ-035 | TC-035-004 | High | P2 | UAT | Sign with expired cert | Signature rejected | Signature accepted | Certificate validation missing | Security | Ready for Retest
DEF-015 | Closed loan still accepts repayment | Loan Servicing | REQ-049 | TC-049-003 | Critical | P1 | SIT | Pay closed loan | Payment rejected | Payment processed | Status validation missing | Business Logic | Assigned
DEF-016 | Early settlement penalty uses outdated rate | Loan Servicing | REQ-045 | TC-045-005 | High | P2 | UAT | Settle after rate change | New rate applied | Old rate applied | Cached calculation | Calculation | In Progress
DEF-017 | Loan statement PDF shows incorrect outstanding balance | Loan Servicing | REQ-047 | TC-047-001 | High | P2 | SIT | Generate statement | Correct balance | Balance mismatch | SQL aggregation defect | Database | New
DEF-018 | Notification history displays duplicate reminders | Loan Servicing | REQ-050 | TC-050-005 | Low | P3 | UAT | Open history | Unique notifications | Duplicates shown | Deduplication missing | Notification | Fixed